## Jira
Summary | Issue key | Issue id | Issue Type | Status | Project key | Project name | Project type | Project lead | Project lead id | Project description | Priority | Resolution | Assignee | Assignee Id | Reporter | Reporter Id | Creator | Creator Id | Created | Updated | Last Viewed | Resolved | Due date | Votes | Description | Environment | Watchers | Watchers Id | Original estimate | Remaining Estimate | Time Spent | Work Ratio | Œ£ Original Estimate | Œ£ Remaining Estimate | Œ£ Time Spent | Security Level | Custom field (Actual end) | Custom field (Actual start) | Custom field (Category) | Custom field (Change reason) | Custom field (Change risk) | Custom field (Change type) | Custom field (Compass) | Custom field (Development) | Custom field (Epic Color) | Custom field (Epic Name) | Custom field (Epic Status) | Custom field (Impact) | Custom field (Issue color) | Custom field (Locked forms) | Custom field (Open forms) | Custom field (Rank) | Custom field (Request Type) | Custom field (Start date) | Custom field (Story point estimate) | Custom field (Submitted forms) | Custom field (Target end) | Custom field (Target start) | Custom field (Team) | Custom field (Total forms) | Custom field ([CHART] Date of First Response) | Comment | Status Category
(MFT) Spelling Error in Transaction Display Message (1.1) | SEN-16 | 10015 | Bug | To Do | SEN | SENG438A1 | software | Raiyan Kabir | 63cabe784ea03a3b2f2fc724 |  | Medium |  |  |  | Jacob Adeyemo | 63cac0f50c615857128e00fc | Jacob Adeyemo | 63cac0f50c615857128e00fc | 2023-01-26T17:41:00.00000005587935450 | 2023-01-26T17:45:00.00000020954757600 | 2023-01-26T17:42:00.00000025145709525 |  |  | 0 | * The function being tested is the withdraw function. The system has been given both valid card and PIN numbers. * After selecting the withdraw option from the main menu, the checking account is selected. * In the withdraw amount options shown, ‚Äú60‚Äù is displayed instead ‚Äú$60‚Äù . |  | Jacob Adeyemo | 63cac0f50c615857128e00fc | [23 empty] | 0¦i00033: | [10 empty] | To Do
Screen Freeze on Deposit into Checking Account (1.0) | SEN-15 | 10014 | Bug | In Progress | SEN | SENG438A1 | software | Raiyan Kabir | 63cabe784ea03a3b2f2fc724 |  | Medium |  |  |  | Jacob Adeyemo | 63cac0f50c615857128e00fc | Jacob Adeyemo | 63cac0f50c615857128e00fc | 2023-01-26T17:35:59.99999970663339225 | 2023-01-26T17:46:59.99999997206032275 | 2023-01-26T17:46:59.99999997206032275 |  |  | 0 | * The function being tested is the deposit function. * The system is on and has received valid input for both card number and PIN number. * The user selects the deposit option(2) from the main menu. * User selects the checking account to be deposited into and inputs $214748358 * The system is expected to update the checking balance. * Instead, the screen freezes. |  | Jacob Adeyemo | 63cac0f50c615857128e00fc | [23 empty] | 0¦i0002v: | [9 empty] | 26/Jan/23 5:47 PM;63cac0f50c615857128e00fc;Defect still exists in version 1.1 | In Progress
Incorrect transaction in Money Market Account (1.0) | SEN-14 | 10013 | Bug | Done | SEN | SENG438A1 | software | Raiyan Kabir | 63cabe784ea03a3b2f2fc724 |  | Medium | Done |  |  | Jacob Adeyemo | 63cac0f50c615857128e00fc | Jacob Adeyemo | 63cac0f50c615857128e00fc | 2023-01-26T17:26:59.99999983236193650 | 2023-01-26T17:32:59.99999974854290475 | 2023-01-26T17:35:59.99999970663339225 | 2023-01-26T17:32:59.99999974854290475 |  | 0 | * The function being tested is the balance inquiry. * The system has been given both valid card and PIN numbers. * The user then selects the inquiry option(4) from the main menu. * User selects money market option. * User withdraws $500 and system is expected to show balance in the money market. * Instead, system shows balance in savings account. |  | Jacob Adeyemo | 63cac0f50c615857128e00fc | [23 empty] | 0¦i0002n: | [10 empty] | Done
(MFT) Login to ATM using Card 1 (1.0) | SEN-13 | 10012 | Bug | Done | SEN | SENG438A1 | software | Raiyan Kabir | 63cabe784ea03a3b2f2fc724 |  | Medium | Done |  |  | Jacob Adeyemo | 63cac0f50c615857128e00fc | Jacob Adeyemo | 63cac0f50c615857128e00fc | 2023-01-26T17:06:59.99999969266355025 | 2023-01-26T17:19:59.9999997206032275 | 2023-01-26T17:06:59.99999969266355025 | 2023-01-26T17:19:59.9999997206032275 |  | 0 | * The function being tested is the login. * The system is on and prompts the user to enter the amount to be dispensed. An input of 1 is given to the system and the system asks the card to be inserted. * A valid card number is given to the system and upon entering an invalid PIN number, the system prompts the user to enter a vild PIN number, which is what is expected from the system. * The user enters an invalid PIN number for the second time. The system prompts the user to enter a valid PIN number, which is what is expected from the system. * Th user then enters a valid PIN number. After entering the valid PIN number, the system still shows an invalid PIN error instead of displaying the main menu as expected. |  | Jacob Adeyemo | 63cac0f50c615857128e00fc | [23 empty] | 0¦i0002f: | [10 empty] | Done
(MFT) System Cannot Establish Connection With bank (1.0) | SEN-12 | 10011 | Bug | Done | SEN | SENG438A1 | software | Raiyan Kabir | 63cabe784ea03a3b2f2fc724 |  | Medium | Done |  |  | Jacob Adeyemo | 63cac0f50c615857128e00fc | Jacob Adeyemo | 63cac0f50c615857128e00fc | 2023-01-26T16:34:59.9999997206032275 | 2023-01-26T17:19:59.9999997206032275 | 2023-01-26T16:48:59.99999994412064550 | 2023-01-26T17:19:59.9999997206032275 |  | 0 | * The function being tested is the deposit function . * The system has been given both valid card and PIN numbers. * The user then selects the deposit option from the main menu. * System failed to deliver ouput that showed a connection to the bank had been established. |  | Jacob Adeyemo | 63cac0f50c615857128e00fc | [23 empty] | 0¦i00027: | [10 empty] | Done
Transfer Error (1.0) | SEN-11 | 10010 | Bug | In Progress | SEN | SENG438A1 | software | Raiyan Kabir | 63cabe784ea03a3b2f2fc724 |  | Medium |  |  |  | Jacob Adeyemo | 63cac0f50c615857128e00fc | Jacob Adeyemo | 63cac0f50c615857128e00fc | 2023-01-22T16:47:00.00000018160789875 | 2023-01-26T17:46:59.99999997206032275 | 2023-01-26T17:46:59.99999997206032275 |  |  | 0 | * The function being tested is the transfer function . * The system has been given both valid card and PIN numbers. * The user then selects the transfer option(3) from the main menu. * User transfers $10 from savings account to checking account. * User receives a message saying "TRANSFER FROM: CHKG to SVGS" indicating the accounts are swapped. * The transfer goes through but instead of $10 the amount transferred is $9.50. * Version 1.1 system transfers correct amount but accounts still swapped on receipt. |  | Jacob Adeyemo | 63cac0f50c615857128e00fc | [23 empty] | 0¦i0001z: | [9 empty] | 26/Jan/23 5:47 PM;63cac0f50c615857128e00fc;Defect still exists in version 1.1 | In Progress
Spelling Error in Transaction Display Message (1.0) | SEN-10 | 10009 | Bug | Done | SEN | SENG438A1 | software | Raiyan Kabir | 63cabe784ea03a3b2f2fc724 |  | Medium | Done |  |  | Jacob Adeyemo | 63cac0f50c615857128e00fc | Jacob Adeyemo | 63cac0f50c615857128e00fc | 2023-01-22T16:34:00.00000015366822150 | 2023-01-26T17:19:59.9999997206032275 | 2023-01-26T17:42:00.00000025145709525 | 2023-01-26T17:19:59.9999997206032275 |  | 0 | * The function being tested is the transaction function. The system has been given both valid card and PIN numbers. * After selecting the withdraw option from the main menu, the checking account is selected. * User enters $40(2) to be withdrawn. * Expected outcome is for the user to get $40 and the amount given by the system is $40. * Upon trying to initiate another transaction the user is greeted with the message "Wood you like to choose another transaction‚Äù. * It should instead say "Would you like to choose another transaction?‚Äù |  | Jacob Adeyemo | 63cac0f50c615857128e00fc | [23 empty] | 0¦i0001r: | [10 empty] | Done
No Saving Option in Balance Inquiry (1.0) | SEN-9 | 10008 | Bug | Done | SEN | SENG438A1 | software | Raiyan Kabir | 63cabe784ea03a3b2f2fc724 |  | Medium | Done |  |  | Jacob Adeyemo | 63cac0f50c615857128e00fc | Jacob Adeyemo | 63cac0f50c615857128e00fc | 2023-01-22T16:27:00.0000000419095125 | 2023-01-26T17:19:59.9999997206032275 | 2023-01-26T17:29:00.00000022351741800 | 2023-01-26T17:19:59.9999997206032275 |  | 0 | * The function being tested is the balance inquiry. * The system has been given both valid card and PIN numbers. * The user then selects the inquiry option(4) from the main menu. * User expects system to show both checking and savings account options. * System only shows checking account option and not a savings account option. |  | Jacob Adeyemo | 63cac0f50c615857128e00fc | [23 empty] | 0¦i0001j: | [10 empty] | Done
Incorrect Transaction in Deposit Function (1.0) | SEN-8 | 10007 | Bug | In Progress | SEN | SENG438A1 | software | Raiyan Kabir | 63cabe784ea03a3b2f2fc724 |  | Medium |  |  |  | Jacob Adeyemo | 63cac0f50c615857128e00fc | Jacob Adeyemo | 63cac0f50c615857128e00fc | 2023-01-22T16:18:00.00000016763806350 | 2023-01-26T17:46:59.99999997206032275 | 2023-01-26T17:46:59.99999997206032275 |  |  | 0 | * The function being tested is the deposit function. * The system is on and has received valid input for both card number and PIN number. * The user selects the deposit option(2) from the main menu. * The user selects the checking account. * The system prompts the user to enter the amount to be deposited, to which the user enter 1 cent. * The expected outcome is for the amount in the users checking account to increase by 1 cent. * Instead $10 is removed from the users checking account. * Version 1.1 removes 10 cents instead of 1 cent |  | Jacob Adeyemo | 63cac0f50c615857128e00fc | [23 empty] | 0¦i0001b: | [9 empty] | 26/Jan/23 5:47 PM;63cac0f50c615857128e00fc;Defect still exists in version 1.1 | In Progress
Withdraw Transaction Screen Freeze (1.0) | SEN-7 | 10006 | Bug | Done | SEN | SENG438A1 | software | Raiyan Kabir | 63cabe784ea03a3b2f2fc724 |  | Medium | Done |  |  | Jacob Adeyemo | 63cac0f50c615857128e00fc | Jacob Adeyemo | 63cac0f50c615857128e00fc | 2023-01-22T16:08:00.000000097788870375 | 2023-01-26T17:19:59.9999997206032275 | 2023-01-26T17:39:00.00000029336660775 | 2023-01-26T17:19:59.9999997206032275 |  | 0 | * The function being tested is the withdraw function. The system has been given both valid card and PIN numbers. * After selecting the withdraw option from the main menu, the checking account is selected. * User enters $40(2) to be withdrawn. * Expected outcome is for the user to get $40 and the amount given to the system is $40. * Afterwards the user tries to withdraw an additional $40. The expected outcome is for the user to receive an extra $40. * Instead the user is shown an insufficient funds message when the user does indeed have sufficient funds. * User then tries to initiate another transaction in which the user expects to be prompted the amount to be withdrawn. * Instead the screen freezes and program has to be restarted. |  | Jacob Adeyemo | 63cac0f50c615857128e00fc | [23 empty] | 0¦i00013: | [10 empty] | Done
Insufficient Funds Error in Withdraw Function (1.0) | SEN-6 | 10005 | Bug | Done | SEN | SENG438A1 | software | Raiyan Kabir | 63cabe784ea03a3b2f2fc724 |  | Medium | Done |  |  | Jacob Adeyemo | 63cac0f50c615857128e00fc | Jacob Adeyemo | 63cac0f50c615857128e00fc | 2023-01-22T15:47:59.9999999580904875 | 2023-01-26T17:20:59.99999991618096825 | 2023-01-26T17:39:00.00000029336660775 | 2023-01-26T17:20:59.99999991618096825 |  | 0 | * The function being tested is the withdraw function. The system has been given both valid card and PIN numbers. * After selecting the withdraw option from the main menu, the checking account is selected. * User enters $40(2) to be withdrawn. * Expected outcome is for the user to get $40 and the amount given by the system is $40. * Afterwards the user tries to withdraw an additional $40. The expected outcome is for the user to receive an extra $40. * Instead the user is shown an insufficient funds message when the user does indeed have sufficient funds. |  | Jacob Adeyemo | 63cac0f50c615857128e00fc | [23 empty] | 0¦i0000v: | [10 empty] | Done
Incorrect Withdraw Amount upon selection (1.0) | SEN-5 | 10004 | Bug | Done | SEN | SENG438A1 | software | Raiyan Kabir | 63cabe784ea03a3b2f2fc724 |  | Medium | Done |  |  | Jacob Adeyemo | 63cac0f50c615857128e00fc | Jacob Adeyemo | 63cac0f50c615857128e00fc | 2023-01-22T15:43:00.00000023748725325 | 2023-01-26T17:20:59.99999991618096825 | 2023-01-22T15:47:59.9999999580904875 | 2023-01-26T17:20:59.99999991618096825 |  | 0 | * The function being tested is the withdraw function. The system has been given both valid card and PIN numbers. * After selecting the withdraw option from the main menu, the checking account is selected. * User enters $20(1) to be withdrawn. * Expected outcome is for the user to get $20. * The amount given by the system is $40. |  | Jacob Adeyemo | 63cac0f50c615857128e00fc | [23 empty] | 0¦i0000n: | [10 empty] | Done
Withdraw Menu Screen Freeze (1.0) | SEN-4 | 10003 | Bug | Done | SEN | SENG438A1 | software | Raiyan Kabir | 63cabe784ea03a3b2f2fc724 |  | Medium | Done |  |  | Jacob Adeyemo | 63cac0f50c615857128e00fc | Jacob Adeyemo | 63cac0f50c615857128e00fc | 2023-01-22T15:24:00.00000029336660775 | 2023-01-26T17:20:59.99999991618096825 | 2023-01-26T17:39:00.00000029336660775 | 2023-01-26T17:20:59.99999991618096825 |  | 0 | * The function being tested is withdraw from the main menu. * The system is on and has received valid input for both card number and PIN number. * The choice selected from the main menu is withdraw (1). * When the user is prompted to select an account from which to withdraw from, an invalid account is given to the system(4). * The expected outcome is for the system to display an error message saying the account selected is invalid. * Instead the screen freezes and the program has to be restarted. |  | Jacob Adeyemo | 63cac0f50c615857128e00fc | [23 empty] | 0¦i0000f: | [10 empty] | Done
Main Menu Screen Freeze (1.0) | SEN-3 | 10002 | Bug | Done | SEN | SENG438A1 | software | Raiyan Kabir | 63cabe784ea03a3b2f2fc724 |  | Medium | Done |  |  | Jacob Adeyemo | 63cac0f50c615857128e00fc | Jacob Adeyemo | 63cac0f50c615857128e00fc | 2023-01-22T15:20:00.00000013969838625 | 2023-01-26T17:20:59.99999991618096825 | 2023-01-26T17:23:00.00000030733644975 | 2023-01-26T17:20:59.99999991618096825 |  | 0 | * The function being tested is the menu. * The system is on and has received valid input for both card number and PIN number. * When the user is prompted to select an option from the menu the user enters an invalid option(e.g 5). * The expected outcome is for the system to display an error message. * Instead the screen freezes and the program has to be restarted. |  | Jacob Adeyemo | 63cac0f50c615857128e00fc | [23 empty] | 0¦i00007: | [10 empty] | Done
Login to ATM using Card 1 (1.0) | SEN-2 | 10001 | Bug | In Progress | SEN | SENG438A1 | software | Raiyan Kabir | 63cabe784ea03a3b2f2fc724 |  | Medium |  |  |  | Jacob Adeyemo | 63cac0f50c615857128e00fc | Jacob Adeyemo | 63cac0f50c615857128e00fc | 2023-01-22T15:11:59.99999983236193650 | 2023-01-26T17:45:59.99999977648258200 | 2023-01-26T17:45:59.99999977648258200 |  |  | 0 | * The function being tested is the login. * The system is on and prompts the user to enter the amount to be dispensed. An input of 1 is given to the system and the system asks the card to be inserted. * A valid card number is given to the system and upon entering an invalid PIN number, the system prompts the user to enter a vild PIN number, which is what is expected from the system. * After entering the valid PIN number, the system still shows an invalid PIN error instead of letting the user make the withdrawal as expected. |  | Jacob Adeyemo | 63cac0f50c615857128e00fc | [23 empty] | 0¦hzzzzz: | [9 empty] | 26/Jan/23 5:46 PM;63cac0f50c615857128e00fc;Defect still exists in version 1.1 | In Progress